## Sheet1
Steps | Category | Task | Due Date | Status | Link
1 | ONOS | MiniNet working | 2018-02-12 | Completed
2 | ONOS | ONOS working | 2018-02-12 | Completed
3 | ONOS | Read ONOS Documentation | 2018-02-12 | In Progress | https://wiki.onosproject.org/display/ONOS/Wiki+Home
4 | ONOS | Use ONOS CLI to "block" traffic or "allow" traffic; similar to what ML Alg will decide
5 | ONOS | Research the Sample Apps provided |  |  | https://wiki.onosproject.org/display/ONOS/Building+the+ONOS+Sample+Apps
6 | ONOS | Research the Template Application |  |  | https://wiki.onosproject.org/display/test/Template+Application+Tutorial
7 | ONOS | Research the Sample PortStatistics Application |  |  | https://wiki.onosproject.org/display/test/Sample+PortStatistics+Application+tutorial+based+on+template+application+tutorial
8 | ONOS | Understand how to extract information about the flows and packet data using ONOS API |  |  | http://api.onosproject.org/1.12.0/
9 | ONOS | Write Java application to extract required information from flows
10 | ONOS | Test Java Application and allow it to "block" traffic and "allow" traffic like ML Alg will decide.
11 | Firewall/IDS | Investigate pfSense or Snort or Pyretic | 2018-02-12
12 | Firewall/IDS | Set up pfSense/Snort/Pyretic talking to Controller | 2018-02-14
13 | Planning | Determine what network topology(s) we will use to test
14 | Mininet | Write Python code for creating Mininet network topology |  |  | https://github.com/mininet/mininet/wiki/Introduction-to-Mininet
15 | Training Data | Select Training Data and Understand what it is telling us |  |  | http://www.unb.ca/cic/datasets/index.html
16 | Training Data | Determine if training data is similar to data we are collecting from ONOS
17 | Training Data | If not similar, determine method to create our own training data
18 | ML Alg | Machine Learning Algorithm (dependent on Training Data)
19 | ML Alg | Connection between our ML Algorithm and our Java code calling the ONOS API
20 | Testing | Test each part of our project and troubleshoot as needed